Tabla para poder hacer costraints del apartado 7.

NOTA: No estoy segura de la colocación de:

* Deliverable Final Report ( lo he colocado en las ultimas tareas, de validation)
* Milestone Project Completion ( no lo he colocado)

|  |  |  |
| --- | --- | --- |
| Activity | Deliverable and due date | Milestone and due date |
| 1.1 Development of the Project management plan | Project management plan  **21/01/22** | Project management plan 5/10/18 |
| 1.2.1 Meetings ( monitoring of the Project) | 21/01/22 |  |
| 1.2.2 Task tracking and scheduling (monitoring of the Project) | 21/01/22 |  |
| 1.3 Annual reporting | 21/01/22 |  |
| 1.4 Project implementation of risk management | 21/01/22 |  |
| 2.1.1 Employment of the necessary staff | 16/11/18 |  |
| 2.1.2 Human resources management | 21/01/22 |  |
| 2.2 Financial plan | 5/10/18 |  |
| 2.3 Documentation management | 21/01/22 |  |
| 2.4 Periodic monitoring | 21/01/22 |  |
| 3.1 State of the art: Payloads | Payload state of the art  21/12/18 | State of the art completion 28/12/18 |
| 3.2 State of the art: Modular system | Modular system state of the art  21/12/18 | State of the art completion 28/12/18 |
| 3.3 State of the art: Urban development applications | Space Applications State of the Art  28/12/18 | State of the art completion 28/12/18 |
| 4.1.1 Payload preliminary design | Payload preliminary design  14/06/19 | Payload preliminary design 14/6/19 |
| 4.1.2 Modular system preliminary design | Modular system preliminary design  6/9/19 | Modular system preliminary design  6/9/19 |
| 4.1.3 Interaction platform preliminary design | Interaction platform preliminary design  29/11/19 | Interaction platform preliminary design  29/11/19 |
| 4.2.1 Payload final design | Payload final design  12/06/20 | Payload final design  12/6/20 |
| 4.2.2 Modular system final design | Modular system final design | Modular system final design 4/9/20 |
| Sensor Data fusion software report  4/9/20 |
| 4.2.3 Interaction platform final design | Interaction platform final design 27/11/20 | Interaction platform final design  27/11/20 |
| Data processing software report 27/11/20 |
| 5.1 Technology demonstrator prototype manufacturing | 16/04/21 | Prototype manufacturing |
| 5.2 Payload validation | Validation  11/06/21 | Individual systems testing 9/7/21 |
| 5.3 Modular system validation | Validation  25/06/21 | Individual systems testing 9/7/21 |
| 5.4 Interaction platform validation | Validation  18/06/21 | Individual systems testing 9/7/21 |
| 5.5 Full system prototype validation | Validation 29/10/21 | Full system testing  29/10/21 |
| Final report |
| 5.6 Quality of the product | Validation 21/01/22 |  |
| Final report |
| 6.1 Exploitation and business plan | Business plan 5/10/18 | Business plan 5/10/18 |
| 7.1 Dissemination and communication plan | Communication plan 5/10/18 | Communication plan  5/10/18 |
| 7.2 On-line dissemination activities | Communication plan 21/01/22 | Communication plan  5/10/18 |
| 7.3 Off-line dissemination activities | Communication plan  21/01/22 | Communication plan  5/10/18 |
| 7.4 Dissemination materials | Communication plan  21/01/22 | Communication plan  5/10/18 |