## PRECEDENCES
TASK LIST |  | PRECEDING TASKS
1 | Project Management
1.1. | Development of the project management plan | 4.1.
1.2. | Monitoring of the Project
1.2.1. | Meetings | 0
1.2.2. | Task tracking and scheduling | 0
1.3. | Annual Reporting
1.4. | Project Implementation of risk management | 3.1., 3.2., 3.3.
2. | Quality and Administration
2.1. | Human resources
2.1.1. | Employment of the necessary staff | 1.1., 2.2.
2.1.2. | Human resources management | 2.1.1.
2.2. | Financial Plan | 4.1.
2.3. | Documentation Management | 0
2.4. | Periodic Monitoring | 0
3. | State of the Art
3.1. | Payloads | 0
3.2. | Modular System | 0
3.3. | Urban Development Applications | 0
4. | Product development
4.1. | Preliminary design
4.1.1. | Payload preliminary design | 3.1., 3.2., 3.3.
4.1.2. | Modular system's preliminary design | 3.1., 3.2., 3.3.
4.1.3. | Interaction platform's preliminary design | 3.1., 3.2., 3.3.
4.2. | Final Design
4.2.1. | Payload final design | 2.1.1.
4.2.2. | Modular system final design | 2.1.1.
4.2.3. | Interaction platform final design | 2.1.1.
5 | Simulation, testing, validation and quality
5.1. | Technology demonstrator prototype manufacturing | 4.2.
5.2. | Payload Validation | 5.1.
5.3. | Modular System Validation | 5.1.
5.4. | Interaction platform validation | 5.1.
5.5. | Full system prototype validation | 5.2., 5.3., 5.4.
5.6. | Quality of the product | 5.5.
6 | Business planning and exploitation of results
6.1. | Market Approach | 4.2.
6.2. | Exploitation and business plans | 5.6.
7 | Communication and dissemination strategies
7.1 | Dissemination and Communication plan | 4.2.
7.2. | On-line dissemination activities | 4.2.
7.3. | Off-line dissemination activities | 4.2.
7.4. | Dissemination materials | 4.2.

## CHRONOGRAM
TASK |  | INCORRECT DURATION OF TASKS
1 | Project Management
1.1. | Development of the project management plan
1.2. | Monitoring of the Project
1.2.1. | Meetings
1.2.2. | Task tracking and scheduling
1.3. | Annual Reporting
1.4. | Project Implementation of risk management
2. | Quality and Administration
2.1. | Human resources
2.1.1. | Employment of the necessary staff
2.1.2. | Human resources management
2.2. | Financial Plan
2.3. | Documentation Management
2.4. | Periodic Monitoring
3. | State of the Art
3.1. | Payloads
3.2. | Modular System
3.3. | Urban Development Applications
4. | Product development
4.1. | Preliminary design
4.1.1. | Payload preliminary design
4.1.2. | Modular system's preliminary design
4.1.3. | Interaction platform's preliminary design
4.2. | Final Design
4.2.1. | Payload final design
4.2.2. | Modular system final design
4.2.3. | Interaction platform final design
5 | Simulation, testing, validation and quality
5.1. | Technology demonstrator prototype manufacturing
5.2. | Payload Validation
5.3. | Modular System Validation
5.4. | Interaction platform validation
5.5. | Full system prototype validation
5.6. | Quality of the product
6 | Business planning and exploitation of results
6.1. | Market Approach
6.2. | Exploitation and business plans
7 | Communication and dissemination strategies
7.1 | Dissemination and Communication plan
7.2. | On-line dissemination activities
7.3. | Off-line dissemination activities
7.4. | Dissemination materials