## Hoja1
Milestone # | Milestone | Related WP | Due Date | Means of Verification
1 | Kick off meeting | WPx | t0
2 | Project management plan | WP1 | t0 + 1
3 | Business plan | WP6 | t0 + 1
4 | Communication plan | WP7 | t0 + 1
5 | State of the art completion | WP3 | t0 + 4
6 | Payload preliminary design | WP4 | t0 + 10
7 | Modular system preliminary design | WP4 | t0 + 13
8 | Interaction platform preliminary design | WP4 | t0 + 16
9 | Payload final design | WP4, WP2 | t0 + 23
10 | Modular system final design | WP4, WP2 | t0 + 26
11 | Interaction platform final design | WP4, WP2 | t0 + 29
12 | Prototype manufacturing | WP4 | t0 + 34
13 | Individual systems testing | WP5 | t0 + 37
14 | Full system testing | WP5 | t0 + 41
15 | Project completion | WPx | t0 + 44
WP1 | MANAGEMENT
WP2 | QUALITY & ADMINISTRATION
WP3 | STATE OF THE ART
WP4 | PRODUCT DEVELOPMENT
WP5 | SIMULATION, TESTING AND VALIDATION
WP6 | BUSINESS PLANNING
WP7 | COMMUNICATION AND DISSEMINATION
WPx | ALL