## Hoja1
TASK LIST |  | PRECEDING TASKS
1 | Project Management | 6.
1.1. | Development of the project management plan
1.2. | Monitoring of the Project
1.2.1. | Meetings
1.2.2. | Task tracking and scheduling
1.3. | Annual Reporting
1.4. | Project Implementation of risk management
2. | Quality and Administration | 1.
2.1. | Human resources
2.1.1. | Employment of the necessary staff
2.1.2. | Human resources management
2.2. | Financial Plan
2.3. | Documentation Management
2.4. | Periodic Monitoring
3. | State of the Art | 0.
3.1. | Payloads
3.2. | Modular System
3.3. | Urban Development Applications
4. | Product development | 1.
4.1. | Preliminary design
4.1.1. | Payload preliminary design
4.1.2. | Modular system's preliminary design
4.1.3. | Interaction platform's preliminary design
4.2. | Final Design
4.2.1. | Payload final design
4.2.2. | Modular system final design
4.2.3. | Interaction platform final design
5 | Simulation, testing, validation and quality | 4.
5.1. | Technology demonstrator prototype manufacturing
5.2. | Payload Validation
5.3. | Modular System Validation
5.4. | Interaction platform validation
5.5. | Full system prototype validation
5.6. | Quality of the product
6 | Business planning and exploitation of results | 3.
6.1. | Market Approach
6.2. | Exploitation and business plans
7 | Communication and dissemination strategies | 5.
7.1 | Dissemination and Communication plan
7.2. | On-line dissemination activities
7.3. | Off-line dissemination activities
7.4. | Dissemination materials