## 4.3
Communication Type | Objective of Communication | Medium | Frequency | Audience | Owner | Deliverable | Format
Internal Status Meetings | Discuss assignments, activities and sharing infromation | Face to Face |  | Project Manager, Business Team, Technical Team | Project Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Technical and Business Status Meetings and Reports |  | Face to Face |  | Business Team, Technical Team | Project Manager | Agenda, Meeting Minutes, Status Reports | Soft copy archived on SharePoint site and project website.
Advisory Committe Meetings | Review progress, risks and issues | Face to Face |  | Project Stakeholders, Project Manager | Project Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Steering Committee Status Meetings |  | Face to Face |  | Steering Committee, Project Manager | Project Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Status Meetings with Stakeholders | Report the status of the project including activities, progress, costs and issues. | Face to Face |  | Stakeholders, Project Manager | Project Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Project Status Reports | Provide Stakeholders information on the status and progress of the project | Email | Regular Intervals | Project Stakeholders, Project Manager | Project Manager | Project status, schedule, budget and cost tracking, status of issues and riskes, health status, status of action items, future or planned activiies
Social Networking | Share any updates on the project | Facebook, Twitter, Intagram | Weekly | General Public
Website | Contain varied information about the project | Website | Updated with any change | General Public
Trade Shows | Face to face contact with potential customers as well as finding new prospects, nurture client relationshps and stay up to date with lastes developments | On site stands | Scheduled | Potential Customers, Genera Public and Industry Professionals
Conferences | Sharing achievements with industry specialists | Conferences | Scheduled | Industry Professionals
Journal Articles | Promoting project ideas, concepts and results in scientific and applied research communities ad getting feedback from relevan stakeholders | Digital and Written platforms |  | Potential Customers, Genera Public and Industry Professionals