## 4.3
Communication Type | Objective of Communication | Medium | Frequency | Audience | Owner | Deliverable | Format
Internal Business Status Meetings | Discuss assignments, activities and sharing information | Face to Face | Weekly | Business Team | Financial Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Technical and Business Status Meetings and Reports | Discuss assignments, activities, sharing information and reporting the project status | Face to Face | Weekly | Project Manager, Business Team, Technical Team, Project Secretary | Project Manager | Agenda, Meeting Minutes, Status Reports | Soft copy archived on SharePoint site and project website.
Advisory Committe Meetings | Review progress, risks and issues | Face to Face | Monthly | Adivsory Committee, Project Stakeholders, Project Manager, Project Secretary | Project Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Steering Committee Status Meetings | Enhance communication and coordination of the project | Face to Face | Monthly | Steering Committee, Project Manager, Project Secretary | Project Manager | Agenda, Meeting Minutes | Soft copy archived on SharePoint site and project website.
Status Meetings and Reports to Stakeholders | Report the status of the project including activities, progress, costs and issues. | Face to Face or Video Conference | Monthly | Stakeholders, Project Manager, Project Secretary | Project Manager | Agenda, Meeting Minutes, Status Reports | Soft copy archived on SharePoint site and project website.
Project Status Reports | Provide Stakeholders information on the status and progress of the project | Email | Monthly | Project Stakeholders, Stakeholder and Procurement Manager, Project Manager | Stakeholder and Procurement Manager | Project status, schedule, budget and cost tracking, status of issues and riskes, health status, status of action items, future or planned activiies | Soft copy archived on SharePoint site and project website.
Social Networking | Share any updates on the project | Facebook, Twitter, Intagram | Weekly | General Public | Marketing and Communication Manager | Online Posts | Online
Website | Contain varied information about the project | Website | Updated with any change | General Public | Marketing and Communication Manager | Online Posts | Online
Trade Shows | Face to face contact with potential customers as well as finding new prospects, nurture client relationshps and stay up to date with lastes developments | On site stands | Scheduled | Potential Customers, Genera Public and Industry Professionals | Marketing and Communication Manager | None | Face to Face
Conferences | Sharing achievements with industry specialists | Conferences | Scheduled | Industry Professionals | Project Manager | Presentation | Face to Face
Journal Articles | Promoting project ideas, concepts and results in scientific and applied research communities ad getting feedback from relevan stakeholders | Digital and Written platforms | When Available | Potential Customers, General Public and Industry Professionals | Project Manager | Journal Article | Hard Copy