## PRECEDENCES
TASK LIST |  | PRECEDING TASKS | PRECEDING TASKS
1 | Project Management |  |  | SS: Start-to-Start
1.1. | Development of the project management plan | 4.1. | SS-0 | FS: Finish-to-start
1.2. | Monitoring of the Project |  | SS-0 | FF: Finish to finish
1.2.1. | Meetings | 0 | SS-0 | SF: Start-to-Finish
1.2.2. | Task tracking and scheduling | 0 | SS-0
1.3. | Annual Reporting |  | SS-0
1.4. | Project Implementation of risk management | 3.1., 3.2., 3.3. | SS-0
2. | Quality and Administration
2.1. | Human resources
2.1.1. | Employment of the necessary staff | 1.1., 2.2. | FS-1.1,2.2
2.1.2. | Human resources management | 2.1.1. | FS-2.1.1
2.2. | Financial Plan | 4.1. | SS-0
2.3. | Documentation Management | 0 | FS-1.1
2.4. | Periodic Monitoring | 0 | FS-1.1
3. | State of the Art
3.1. | Payloads | 0 | FS-1.1,
3.2. | Modular System | 0 | FS-1.1,
3.3. | Urban Development Applications | 0 | FS-1.1,
4. | Product development
4.1. | Preliminary design
4.1.1. | Payload preliminary design | 3.1., 3.2., 3.3. | SF-3.1
4.1.2. | Modular system's preliminary design | 3.1., 3.2., 3.3. | SF-3.2
4.1.3. | Interaction platform's preliminary design | 3.1., 3.2., 3.3. | SF-3.3
4.2. | Final Design
4.2.1. | Payload final design | 2.1.1. | SF-4.1.1
4.2.2. | Modular system final design | 2.1.1. | SF-4.1.2
4.2.3. | Interaction platform final design | 2.1.1. | SF-4.1.3
5 | Simulation, testing, validation and quality
5.1. | Technology demonstrator prototype manufacturing | 4.2. | SF-4.2
5.2. | Payload Validation | 5.1. | SF-5.1
5.3. | Modular System Validation | 5.1. | SF-5.1
5.4. | Interaction platform validation | 5.1. | SF-5.1
5.5. | Full system prototype validation | 5.2., 5.3., 5.4. | SF-5.2,5.3,5.4
5.6. | Quality of the product | 5.5. | SF-5.5
6 | Business planning and exploitation of results
6.1. | Market Approach | 4.2. | SS-0
6.2. | Exploitation and business plans | 5.6. | SS-0
7 | Communication and dissemination strategies
7.1 | Dissemination and Communication plan | 4.2. | SS-0
7.2. | On-line dissemination activities | 4.2. | SS-0
7.3. | Off-line dissemination activities | 4.2. | SS-0
7.4. | Dissemination materials | 4.2. | SS-0
MILESTONES
0 | Quick Off meeting
0.1 | Project management plan |  | FF-1.1
0.2 | Business plan
0.3 | Communication plan
0.4 | State of the art report
0.5 | Payload preliminary desing
0.6 | Modular system preliminary design
0.7 | Interaction platform preliminary design
0.8 | Mid-term project report
0.9 | Payload final design
0.10 | Modular system final design
0.11 | Interaction platform final design
0.12 | Prototype manufacturing
0.13 | Individual systems testing
0.14 | Full system testing
0.15 | Final report

## CHRONOGRAM
TASK |  | INCORRECT DURATION OF TASKS
1 | Project Management
1.1. | Development of the project management plan
1.2. | Monitoring of the Project
1.2.1. | Meetings
1.2.2. | Task tracking and scheduling
1.3. | Annual Reporting
1.4. | Project Implementation of risk management
2. | Quality and Administration
2.1. | Human resources
2.1.1. | Employment of the necessary staff
2.1.2. | Human resources management
2.2. | Financial Plan
2.3. | Documentation Management
2.4. | Periodic Monitoring
3. | State of the Art
3.1. | Payloads
3.2. | Modular System
3.3. | Urban Development Applications
4. | Product development
4.1. | Preliminary design
4.1.1. | Payload preliminary design
4.1.2. | Modular system's preliminary design
4.1.3. | Interaction platform's preliminary design
4.2. | Final Design
4.2.1. | Payload final design
4.2.2. | Modular system final design
4.2.3. | Interaction platform final design
5 | Simulation, testing, validation and quality
5.1. | Technology demonstrator prototype manufacturing
5.2. | Payload Validation
5.3. | Modular System Validation
5.4. | Interaction platform validation
5.5. | Full system prototype validation
5.6. | Quality of the product
6 | Business planning and exploitation of results
6.1. | Market Approach
6.2. | Exploitation and business plans
7 | Communication and dissemination strategies
7.1 | Dissemination and Communication plan
7.2. | On-line dissemination activities
7.3. | Off-line dissemination activities
7.4. | Dissemination materials